## Housing
Is the project likely to involve Construction work? See SP15 CDM Procedure for definition of Construction Work |  | No |  | CDM does not apply
Yes
Is the project likely to involve more than one contractor? |  | No
Yes
CDM applies. EO or delegated appointed person becomes the Client for the project. |  | Pre-Construction Phase | CDM applies. EO or delegated appointed person becomes the Client for the project.
Housing appoints a competent Principal Designer |  |  | Housing appoints a competent internal or external Designer. E.G. Derek Lyon (PM Projects) or Ewing Somerville LTD for external works. |  | Client Brief / Tender Pack prepared.
Housing and/or Principal Designer appoints competent Designers |  |  | CHECK POINT: Inform Health and Safety Service of project.
CHECK POINT: Inform Health and Safety Service of project |  |  | Housing provides pre-construction information to Designer (See C01 PCI for further information)
Housing provides pre-construction information to Principal Designer and Designers |  |  | Complete design.
Principal Designer starts development of the Health and Safety File |  |  | Housing appoints a competent Contractor (Internal or External)
Procurement Phase
Housing notifies HSE via Form F10 if project is notifiable |  |  | Housing notifies HSE via Form F10 if project is notifiable (See SP15 CDM for further detail)
Housing appoints competent Principal Contractor. |  |  | CHECK POINT: Contact Health and Safety Service for pre-construction information approval |  | Service to liaise with H&S for support in the completion of the C01 PCI document
CHECK POINT: Contact Health and Safety Service for pre-construction information approval |  |  | Housing provides pre-construction information to Contractor
Principal Designer provides pre-construction information to Principal Contractor. |  |  | Contractor prepares Construction Phase Health and Safety Plan (CPP) |  | Where Contractor is internal, H&S to assist in the preperation of the C02 CPP document
Principal Contractor prepares Construction Phase Health and Safety Plan (CPP) |  |  | CHECK POINT: Health and Safety Service to approve CPP
CHECK POINT: Health and Safety Service to approve CPP |  |  | Housing verifies CPP is sufficiently developed to start work.
Housing verifies CPP is sufficiently developed to start work. |  |  | CHECK POINT: Health and Safety Service to approve Contractor High Risk Activity RA/MS via D03 Review Form |  | High risk activities as per Appendix 8 of SP15 CDM
CHECK POINT: Health and Safety Service to approve Contractor High Risk Activity RA/MS via D03 Review Form
Carry out work. |  | Construction Phase | Carry out work.
Principal Contractor collects information for Health and Safety File
Principal Designer modifies existing or produces new Health & Safety File and gives it to the Housing. |  | Post Construction Phase | Housing amends existing Health & Safety File (if appropriate). |  | Liaise with H&S for the completion of the C03 Health and Safety File document

## Estates
Is the project likely to involve Construction work? See SP15 CDM Procedure for definition of Construction Work |  | No |  | CDM does not apply
Yes
Is the project likely to involve more than one contractor? |  | No
Yes
CDM applies. EO or delegated appointed person becomes the Client for the project. |  | Pre-Construction Phase | CDM applies. EO or delegated appointed person becomes the Client for the project.
Estates appoints a competent Principal Designer |  |  | Estates appoints a competent internal or external Designer. |  | Client Brief / Tender Pack prepared.
Estates and/or Principal Designer appoints competent Designers |  |  | CHECK POINT: Inform Health and Safety Service of project.
CHECK POINT: Inform Health and Safety Service of project |  |  | Estates provides pre-construction information to Designer (See C01 PCI for further information)
Estates provides pre-construction information to Principal Designer and Designers |  |  | Complete design.
Principal Designer starts development of the Health and Safety File |  |  | Estates appoints a competent Contractor (Internal or External)
Procurement Phase
Estates notifies HSE via Form F10 if project is notifiable |  |  | Estates notifies HSE via Form F10 if project is notifiable (See SP15 CDM for further detail)
Estates appoints competent Principal Contractor. |  |  | CHECK POINT: Contact Health and Safety Service for pre-construction information approval |  | Service to liaise with H&S for support in the completion of the C01 PCI document
CHECK POINT: Contact Health and Safety Service for pre-construction information approval |  |  | Estates provides pre-construction information to Contractor
Principal Designer provides pre-construction information to Principal Contractor. |  |  | Contractor prepares Construction Phase Health and Safety Plan (CPP) |  | Where Contractor is internal, H&S to assist in the preperation of the C02 CPP document
Principal Contractor prepares Construction Phase Health and Safety Plan (CPP) |  |  | CHECK POINT: Health and Safety Service to approve CPP
CHECK POINT: Health and Safety Service to approve CPP |  |  | Estates verifies CPP is sufficiently developed to start work.
Estates verifies CPP is sufficiently developed to start work. |  |  | CHECK POINT: Health and Safety Service to approve Contractor High Risk Activity RA/MS via D03 Review Form |  | High risk activities as per Appendix 8 of SP15 CDM
CHECK POINT: Health and Safety Service to approve Contractor High Risk Activity RA/MS via D03 Review Form
Carry out work. |  | Construction Phase | Carry out work.
Principal Contractor collects information for Health and Safety File
Principal Designer modifies existing or produces new Health & Safety File and gives it to the Estates. |  | Post Construction Phase | Estates amends existing Health & Safety File (if appropriate). |  | Liaise with H&S for the completion of the C03 Health and Safety File document

## Assets
Is the project likely to involve Construction work? See SP15 CDM Procedure for definition of Construction Work |  | No |  | CDM does not apply
Yes
Is the project likely to involve more than one contractor? |  | No
Yes
CDM applies. EO or delegated appointed person becomes the Client for the project. |  | Pre-Construction Phase | CDM applies. EO or delegated appointed person becomes the Client for the project.
Assets appoints a competent Principal Designer |  |  | Assets appoints a competent internal or external Designer. |  | Client Brief / Tender Pack prepared.
Assets and/or Principal Designer appoints competent Designers |  |  | CHECK POINT: Inform Health and Safety Service of project.
CHECK POINT: Inform Health and Safety Service of project |  |  | Assets provides pre-construction information to Designer (See C01 PCI for further information)
Assets provides pre-construction information to Principal Designer and Designers |  |  | Complete design.
Principal Designer starts development of the Health and Safety File |  |  | Assets appoints a competent Contractor (Internal or External)
Procurement Phase
Assets notifies HSE via Form F10 if project is notifiable |  |  | Assets notifies HSE via Form F10 if project is notifiable (See SP15 CDM for further detail)
Assets appoints competent Principal Contractor. |  |  | CHECK POINT: Contact Health and Safety Service for pre-construction information approval |  | Service to liaise with H&S for support in the completion of the C01 PCI document
CHECK POINT: Contact Health and Safety Service for pre-construction information approval |  |  | Assets provides pre-construction information to Contractor
Principal Designer provides pre-construction information to Principal Contractor. |  |  | Contractor prepares Construction Phase Health and Safety Plan (CPP) |  | Where Contractor is internal, H&S to assist in the preperation of the C02 CPP document
Principal Contractor prepares Construction Phase Health and Safety Plan (CPP) |  |  | CHECK POINT: Health and Safety Service to approve CPP
CHECK POINT: Health and Safety Service to approve CPP |  |  | Assets verifies CPP is sufficiently developed to start work.
Assets verifies CPP is sufficiently developed to start work. |  |  | CHECK POINT: Health and Safety Service to approve Contractor High Risk Activity RA/MS via D03 Review Form |  | High risk activities as per Appendix 8 of SP15 CDM
CHECK POINT: Health and Safety Service to approve Contractor High Risk Activity RA/MS via D03 Review Form
Carry out work. |  | Construction Phase | Carry out work.
Principal Contractor collects information for Health and Safety File
Principal Designer modifies existing or produces new Health & Safety File and gives it to the Assets. |  | Post Construction Phase | Assets amends existing Health & Safety File (if appropriate). |  | Liaise with H&S for the completion of the C03 Health and Safety File document

## Major Assets
Is the project likely to involve Construction work? See SP15 CDM Procedure for definition of Construction Work |  | No | CDM does not apply
Yes
Is the project likely to involve more than one contractor?
Yes
CDM applies. EO or delegated appointed person becomes the Client for the project. |  | Pre-Construction Phase
Major Assets appoints a competent Principal Designer |  | Client Brief/Works Information/Tender Pack prepared. Liaise with H&S for design risk management advice where applicable
Major Assets and/or Principal Designer appoints competent Designers
CHECK POINT: Inform/email Health and Safety Service of project |  | Liaise with H&S for regular design and pre-planning meetings if required
Major Assets provides pre-construction information to Principal Designer and Designers
Principal Designer starts development of the Health and Safety File
Procurement Phase
Major Assets notifies HSE via Form F10 if project is notifiable
Major Assets appoints competent Principal Contractor.
CHECK POINT: Contact Health and Safety Service for pre-construction information approval |  | Service to liaise with H&S for support in the completion of the C01 PCI document where applicable. Any externally completed PCI information must be passed to H&S for review
Principal Designer provides pre-construction information to Principal Contractor.
Principal Contractor prepares Construction Phase Health and Safety Plan (CPP)
CHECK POINT: Health and Safety Service to review and approve CPP
Major Assets verifies CPP is sufficiently developed to start work.
Carry out work. |  | Construction Phase
Principal Contractor collects information for Health and Safety File
Principal Designer modifies existing or produces new Health & Safety File and gives it to the Major Assets. |  | Post Construction Phase |  | Liaise with H&S for the completion of the C03 Health and Safety File document if required

## Property Maintenance
Is the project likely to involve Construction work? See SP15 CDM Procedure for definition of Construction Work |  | No |  | CDM does not apply
Please note: PM acts a PC or Contractor only
Yes
Is the project likely to involve more than one contractor? |  | No
Yes
CDM applies. EO or delegated appointed person becomes the Client (other services within the council) for the project. |  | Pre-Construction Phase | CDM applies. EO or delegated appointed person becomes the Client for the project.
Client appoints a competent Principal Designer |  |  | Client appoints a competent Designer |  | Client Brief / Tender Pack prepared.
Client and/or Principal Designer appoints competent Designers |  |  | CHECK POINT: Client informs Health and Safety Service of project.
CHECK POINT: Client informs Health and Safety Service of project. |  |  | Client provides pre-construction information to Designer (See C01 PCI for further information)
Client provides pre-construction information to Principal Designer and Designers |  |  | Complete design.
Principal Designer starts development of the Health and Safety File |  |  | Client appoints Property Maintenance as sole contractor
Procurement Phase
Client notifies HSE via Form F10 if project is notifiable |  |  | Client notifies HSE via Form F10 if project is notifiable (See SP15 CDM for further detail)
Client appoints Property Maintenance as Principal Contractor for the project |  |  | CHECK POINT: Contact Health and Safety Service for pre-construction information approval |  | Client to liaise with H&S for support in the completion of the C01 PCI document
CHECK POINT: Contact Health and Safety Service for pre-construction information approval |  |  | Client provides pre-construction information to Property Maintenance
Principal Designer provides pre-construction information to Property Maintenance |  |  | Property Maintenance prepares Construction Phase Health and Safety Plan (CPP) |  | H&S to assist in the preparation of the C02 CPP document and detail the task specific risk assessments and SSOW for high risk activities
Property Maintenance prepares Construction Phase Health and Safety Plan (CPP) |  |  | CHECK POINT: Health and Safety Service to approve CPP
Property Maintenance to appoint competent contractors where applicable
CHECK POINT: Health and Safety Service to approve CPP |  |  | Client verifies CPP is sufficiently developed to start work.
Client verifies CPP is sufficiently developed to start work. |  |  | CHECK POINT: Health and Safety Service to aid in the completion of any additional risk assessments where required. |  | High risk activities as per Appendix 8 of SP15 CDM
CHECK POINT: Health and Safety Service to approve Contractor High Risk Activity RA/MS via D03 Review Form
Carry out work. |  | Construction Phase | Carry out work.
Property Maintenance collects information for Health and Safety File
Principal Designer modifies existing or produces new Health & Safety File and gives it to the Client. |  | Post Construction Phase | Client amends existing Health & Safety File (if appropriate). |  | Liaise with H&S for the completion of the C03 Health and Safety File document

## R&E
Is the project likely to involve Construction work? See SP15 CDM Procedure for definition of Construction Work |  | No |  | CDM does not apply
Please note: Roads & Enviroment acts as Client, PC or Contractor, for acting as Client, please follow tab 2 for R&E
Yes
Is the project likely to involve more than one contractor? |  | No
Yes
CDM applies. EO or delegated appointed person becomes the Client (other services within the council) for the project. |  | Pre-Construction Phase | CDM applies. EO or delegated appointed person becomes the Client for the project.
Client appoints a competent Principal Designer |  |  | Client appoints a competent Designer |  | Client Brief / Tender Pack prepared.
Client and/or Principal Designer appoints competent Designers |  |  | CHECK POINT: Client informs Health and Safety Service of project.
CHECK POINT: Client informs Health and Safety Service of project. |  |  | Client provides pre-construction information to Designer (See C01 PCI for further information)
Client provides pre-construction information to Principal Designer and Designers |  |  | Complete design.
Principal Designer starts development of the Health and Safety File |  |  | Client appoints Roads as sole contractor
Procurement Phase
Client notifies HSE via Form F10 if project is notifiable |  |  | Client notifies HSE via Form F10 if project is notifiable (See SP15 CDM for further detail)
Client appoints Roads as Principal Contractor for the project |  |  | CHECK POINT: Contact Health and Safety Service for pre-construction information approval |  | Client to liaise with H&S for support in the completion of the C01 PCI document
CHECK POINT: Contact Health and Safety Service for pre-construction information approval |  |  | Client provides pre-construction information to Roads
Principal Designer provides pre-construction information to R&E |  |  | R&E prepares Construction Phase Health and Safety Plan (CPP) |  | H&S to assist in the preperation of the C02 CPP document and detail the task specific risk assessments and SSOW for high risk activities
R&E prepares Construction Phase Health and Safety Plan (CPP) |  |  | CHECK POINT: Health and Safety Service to approve CPP
R&E to appoint competent contractors where applicable
CHECK POINT: Health and Safety Service to approve CPP |  |  | Client verifies CPP is sufficiently developed to start work.
Client verifies CPP is sufficiently developed to start work. |  |  | CHECK POINT: Health and Safety Service to aid in the completion of any additional risk assessments where required. |  | High risk activities as per Appendix 8 of SP15 CDM
CHECK POINT: Health and Safety Service to approve Contractor High Risk Activity RA/MS via D03 Review Form
Carry out work. |  | Construction Phase | Carry out work.
R&E collects information for Health and Safety File
Principal Designer modifies existing or produces new Health & Safety File and gives it to the Client. |  | Post Construction Phase | Client amends existing Health & Safety File (if appropriate). |  | Liaise with H&S for the completion of the C03 Health and Safety File document

## R&E as Client
Is the project likely to involve Construction work? See SP15 CDM Procedure for definition of Construction Work |  | No |  | CDM does not apply
Yes
Is the project likely to involve more than one contractor? |  | No
Yes
CDM applies. EO or delegated appointed person becomes the Client for the project. |  | Pre-Construction Phase | CDM applies. EO or delegated appointed person becomes the Client for the project.
R&E appoints a competent Principal Designer |  |  | R&E appoints a competent internal or external Designer. |  | Client Brief / Tender Pack prepared.
R&E and/or Principal Designer appoints competent Designers |  |  | CHECK POINT: Inform Health and Safety Service of project.
CHECK POINT: Inform Health and Safety Service of project |  |  | R&E provides pre-construction information to Designer (See C01 PCI for further information)
R&E provides pre-construction information to Principal Designer and Designers |  |  | Complete design.
Principal Designer starts development of the Health and Safety File |  |  | R&E appoints a competent Contractor (Internal or External)
Procurement Phase
R&E notifies HSE via Form F10 if project is notifiable |  |  | R&E notifies HSE via Form F10 if project is notifiable (See SP15 CDM for further detail)
R&E appoints competent Principal Contractor. |  |  | CHECK POINT: Contact Health and Safety Service for pre-construction information approval |  | Service to liaise with H&S for support in the completion of the C01 PCI document
CHECK POINT: Contact Health and Safety Service for pre-construction information approval |  |  | R&E provides pre-construction information to Contractor
Principal Designer provides pre-construction information to Principal Contractor. |  |  | Contractor prepares Construction Phase Health and Safety Plan (CPP) |  | Where Contractor is internal, H&S to assist in the preperation of the C02 CPP document
Principal Contractor prepares Construction Phase Health and Safety Plan (CPP) |  |  | CHECK POINT: Health and Safety Service to approve CPP
CHECK POINT: Health and Safety Service to approve CPP |  |  | R&E verifies CPP is sufficiently developed to start work.
R&E verifies CPP is sufficiently developed to start work. |  |  | CHECK POINT: Health and Safety Service to approve Contractor High Risk Activity RA/MS via D03 Review Form |  | High risk activities as per Appendix 8 of SP15 CDM
CHECK POINT: Health and Safety Service to approve Contractor High Risk Activity RA/MS via D03 Review Form
Carry out work. |  | Construction Phase | Carry out work.
Principal Contractor collects information for Health and Safety File
Principal Designer modifies existing or produces new Health & Safety File and gives it to the R&E. |  | Post Construction Phase | R&E amends existing Health & Safety File (if appropriate). |  | Liaise with H&S for the completion of the C03 Health and Safety File document

## Planning & Development
Is the project likely to involve Construction work? See SP15 CDM Procedure for definition of Construction Work |  | No | CDM does not apply
Yes
Is the project likely to involve more than one contractor?
Yes
CDM applies. EO or delegated appointed person becomes the Client for the project. |  | Pre-Construction Phase
Learning & Development appoints a competent Principal Designer |  | Client Brief/Works Information/Tender Pack prepared. Liaise with H&S for design risk management advice where applicable
Learning & Development and/or Principal Designer appoints competent Designers
CHECK POINT: Inform/email Health and Safety Service of project |  | Liaise with H&S for regular design and pre-planning meetings if required
Learning & Development provides pre-construction information to Principal Designer and Designers
Principal Designer starts development of the Health and Safety File
Procurement Phase
Learning & Development notifies HSE via Form F10 if project is notifiable
Learning & Development appoints competent Principal Contractor.
CHECK POINT: Contact Health and Safety Service for pre-construction information approval |  | Service to liaise with H&S for support in the completion of the C01 PCI document where applicable. Any externally completed PCI information must be passed to H&S for review
Principal Designer provides pre-construction information to Principal Contractor.
Principal Contractor prepares Construction Phase Health and Safety Plan (CPP)
CHECK POINT: Health and Safety Service to review and approve CPP
Learning & Development verifies CPP is sufficiently developed to start work.
Carry out work. |  | Construction Phase
Principal Contractor collects information for Health and Safety File
Principal Designer modifies existing or produces new Health & Safety File and gives it to the Learning & Development. |  | Post Construction Phase |  | Liaise with H&S for the completion of the C03 Health and Safety File document if required